## Summary
Phase | Breakup | Effort (Person days) | Deliverables
Analysis | 20% | 31.4286
Build and Unit Testing | 35% | 55 | Test plan and Test cases
System Integration/Regression Testing | 30% | 47.1429
User Testing Support | 10% | 15.7143 | Deployment document
Deployment | 5% | 7.8571
Additional line items
Performance testing |  | 5
Transition to support (ops support documentation) |  | 3
Additional Deployment Support |  | 5
Base Effort (Person Days) |  | 170.1429
PM/CM | 10% | 17.0143
Contingency | 20% | 34.0286
Total effort (Person days) |  | 221.1857

## Build Effort
Sr.No | Effort line items | Effort(Person days)
Analysis
1 | Identify different Plugins/On premise server approach used in the print preview | 4
2 | Analyse the functionality of components used for print pdf | 6
3 | Identify security constraints in using the components specified in #1 | 4
4 | Analysis on Offline usage of the print preview | 3
5 | Analysis Merging PDF's in to Master PDF | 4
6 | Analysis on adding comments to PDF | 4
7 | Feasibility to integrate with Document Management System/iManage | 6
Build
4 | Authentication to the Chrome profile | 3
5 | Capturing the content of the authenticated urls | 3
6 | Develop chrome extension components | 2
7 | Styling of chrome extension components | 1
8 | Error handling (showing error messages,clearing the generated PDF if any error) | 3
9 | Integrate with Chrome PDF viewer plugin | 5
10 | Generate PDF for the URLs | 4
11 | Accessing file system of the user | 3
12 | Implementing the functionality of Save the PDF | 4
13 | Supressing the existing print functionality to bypass print preview | 3
14 | Provision to print generated PDF | 3
15 | Unit testing extension on different operating systems (Windows/Mac/Android/Iphone) | 6
16 | Integrate with iManage | 15
Total Build effort (G13:G25) |  | 55

## Assumptions and dependencies
Dependencies |  | Assumptions
1 | Depends on pdf viewer extension | 1 | In any case using chrome extension alone doesn’t suffice the requirement, build a custom service to convert the given html to pdf
2 | Depends on the server side components such as ItextPDF, rendered XHTML etc (if custom service is chosen) | 2 | Convert given html to pdf may not work if the webpage needs authentication
|  | 3 | Extension should work on dev.pwc.com and pwc.com domain
|  | 4 | Implementation using chrome extension or custom service (using Java) will be finalized prior to build phase
|  | 5 | On premise server will be used to host the custom built application
Questions
1 | What are the elements to be provisioned in the extension UI?