## Buy
| Description | Cost | Constraints
1 | Free Chrome Extension | Free
Not All Sites, possible. Legal Constraints
No Support - Use as is
May be adds from print-Friendly
PwC Compliance - Clearance
Security Testing to be carried out
2 | Server (Print Friend Pro) | $100 per year
Not sure how it works for end browser extensions

## Build
|  | Person Days | Comments
1 | Analaysis | 6
1.1 | Collect Sample Sites | 1
1.2 | Analyze Security Constraints | 2
1.3 | Validate iManage | 2
1.4 | Offline Usage of the App | 1
2 | Develop | 40
2.1 | Plugin Development | 20
2.2 | Filter out Ads and noise | 10
2.3 | Save as PDF | 5
2.4 | Enable Print Functionality | 5
2.5
3 | Testing | 43
3.1 | Test on multiple Chrome versions | 6 | 3 versions
3.2 | Test on multiple Operating Systems (Windows, Mac, Android and iPhone) | 12 | 4 Flavours * 3 days each
3.3 | Clearing Security Tests | 10
3.4 | Performance Tests | 10
3.5 | Multiple Browser Simultaneous Tests in a machine | 5
3.6
4 | Deployment | 23
4.1 | Packaging Product | 3
4.2 | Clearing internal Chrome Extensions Clearance | 10
4.3 | Hosting on Google Extension Server | 5
4.4 | Deployment Test | 5
4.5
5 | Support | 25
5.1 | UAT | 5
5.2 | Post Production Support | 20 | 1 Month
5.3
5.4
| Total Effort | 137 | Person Days